## Sheet1
DD | DTM | What | Why | When
X |  | Merge R2 0204 DD into R3 | Currently, R3 DD is based on R2 DD 0202. There are multiple bugs in it where menus were not rendered correctly, methods didn't work, etc. Appears to have never been tested at all. DeltaV interoperability lab was first to point it out. Additionally, FD alerts can't be configured from a DD | Necessary to begin R3-specific work
X | X | Provide menus to configure enhanced data collection | New functionality | In coordination to PST testing and data collection testing
X | X | Provide menus to configure and start PST | New functionality | In coordination to PST testing and data collection testing
| X | Remove 60 s limit on diagnostic test | Fix data retrieval bugs | ASAP
| X | GUI to retrieve and parse diagnostic buffer regardless of who and how started a procedure | PST support Enhanced data collection support Quality improvenet | In coordination to PST testing and data collection testing
X | X | Provide UI to display physical analog input (known as PV in HART products) | New functionality | To support testing
X | X | Support for DO FB channel FAULT DO and TB are affected | New functionality | To support testing
X |  | Remove override of TB and RB modes | Bug fix | before final testing
| X | Display correct FW rev. on Update FW dialog | Bug fix | before final testing
X | X | Enhance presentation of alerts | New enum | ASAP
X |  | Populate no_download_ptb, upload_wanted_ptb | Missing functionality | Required before interoperability testing