## trunk part(R2 and R3)(to do)
ID | Work Item Type | Title | Assigned To | State
24705 | BugReport | Downgrade(R1 RC15->R2 Beta1) via FF failed | Li, Joan (BHGE) | Resolved
24750 | BugReport | *FF FP -- A trap doesn't make it to alerts log | Kostadinov, Vladimir | In Review
24876 | BugReport | <UC45 Flash data integrity self-test at FFP> need re-design | Kostadinov, Vladimir | In Review
24989 | Task | Test Beta 2 | Kostadinov, Vladimir | Finished
25044 | BugReport | *FF FFP -- fbs_write_param_loc() fails without notification if startup_sync==TRUE | Kostadinov, Vladimir | Resolved
25148 | BugReport | *FF -- Back-calculation of limit status of valve position is incorrect in DO FB | Hu, Helen | Resolved
25184 | BugReport | UC45: TB Init Time is 2000000s and target mode is Manual as default. | Kostadinov, Vladimir | Resolved
25203 | BugReport | ITK Test case i3700_05 fails when executed twice in a row | Kostadinov, Vladimir | In Review
25239 | BugReport | *FF AP -- FW Loader -- Useful optimizations | Kostadinov, Vladimir | Resolved
25305 | BugReport | TB doesn't allow transition to AUTO mode if FINAL_VALUE.... is not GOOD | Kostadinov, Vladimir | Resolved
25347 | BugReport | Default Values for Function Blocks | Kostadinov, Vladimir | Resolved
25348 | BugReport | *FFP - Implement FB profiling instrumentation | Hu, Helen | Resolved
25349 | BugReport | *FFP -- Implement generic HART slave for commands intercepted by FFP | Kostadinov, Vladimir | Resolved
25368 | Task | Back-port changes from Release 2 branch up to changeset 53116 | Kostadinov, Vladimir | Finished
25425 | BugReport | FF Firmare: Advanced Key still will be lost during firmware upgrade or downgrade | Kostadinov, Vladimir | Deferred
25464 | BugReport | *FF FP -- Incorrect constants | Kostadinov, Vladimir | Resolved
25535 | BugReport | *FFP -- Infrastructure improvements -- NVMEM management should be like in APP | Kostadinov, Vladimir | Resolved
25601 | BugReport | *FFP -- duplication or redefinition APP's selftune.h constants | Kostadinov, Vladimir | Resolved
25628 | BugReport | *FF FFP -- Alerts -- Restore the functionality lost with modified mn_advanced | Kostadinov, Vladimir | Resolved
25717 | Requirement | *FF FFP -- MN NVMEM should support automatic reinitialization to defaults per record | Kostadinov, Vladimir | Resolved
25731 | Task | *FFP -- NVMEM management -- Add a method of saving a log file without a running process | Kostadinov, Vladimir | Finished
26097 | Requirement | *FF -- Implement Partial Stroke Test | Kostadinov, Vladimir | Resolved
26098 | BugReport | *FF -- Implement basic framework for PST in APP | Kostadinov, Vladimir | Resolved
26099 | BugReport | *FF -- APP -- Setpoint presentation in local UI may be incorrect | Khasin, Ark | In Review
26100 | BugReport | *FF -- Potential artificial windup of control application | Kostadinov, Vladimir | New
26101 | BugReport | *FF -- APP -- Inaccurate compile-time conversions | Kostadinov, Vladimir | Resolved
26102 | BugReport | *FF -- APP -- Multiple definitions of open stop adjustment limits | Kostadinov, Vladimir | Resolved
26141 | BugReport | Saved signature data don't match the buffer | Kostadinov, Vladimir | Resolved
26167 | Requirement | *FF AP -- Strong typing -- control deadzone shall be of position type | Kostadinov, Vladimir | Resolved
26168 | Requirement | *FF -- APP -- Strong typing - position and pressure noise shall be of position and pressure types, respectively | Kostadinov, Vladimir | Resolved
26170 | BugReport | *FF -- APP -- mix-up of position in linearized sensor domain and %range domain | Kostadinov, Vladimir | Resolved
26171 | Requirement | *FF -- PST completion shall distinguish between "canceled" and "failed" | Kostadinov, Vladimir | Resolved
26226 | Requirement | *FF -- FFP -- TB discrete final values must not be stored in NVMEM | Kostadinov, Vladimir | Resolved
26227 | Requirement | *FF -- FFP -- TB paramters should have a single entry point for DD and GW scripts | Kostadinov, Vladimir | Resolved
26238 | BugReport | *FF -- GW scripts -- Erroneous or inconsistent entries in GW script | Kostadinov, Vladimir | Resolved
26312 | BugReport | * FF FFP and APP -- NVRAM repair on start will almost never be invoked | Kostadinov, Vladimir | Resolved
26325 | Requirement | *FF -- NVRAM -- Provide functionality to support deferred writes | Kostadinov, Vladimir | Resolved
26349 | Requirement | *FFP -- TB static revision management | Kostadinov, Vladimir | Resolved
26398 | Requirement | *FF APP -- Provide framework for event-triggered high-speed data collection | Khasin, Ark | Resolved
26424 | Requirement | *FF -- Quality -- APP firmware should include event-driven tasks in watchdog monitoring | Hu, Helen | Resolved
26425 | Requirement | *FF -- Quality -- APP and FFP functionality, when common, should use the same code | Kostadinov, Vladimir | Resolved
26431 | BugReport | *FFP -- NVMEM management -- provide framework for NVMEM translation on activation | Kostadinov, Vladimir | Resolved
26446 | BugReport | *FF FFP -- Refactored NVRAM interface usually fails on reset, causing full reinitialization of FFP | Hu, Helen | Resolved
26453 | BugReport | *FF -- Watchdog -- Pattern of checked-in tasks is not saved with the watchdog trap | Hu, Helen | Resolved
26629 | BugReport | *FF -- PST -- No method to suppress control deadzone for the running process | Kostadinov, Vladimir | Resolved
26633 | BugReport | *FF -- FFP -- "Advanced" parameter is disabled | Hu, Helen | Resolved
26634 | BugReport | *FF -- APP -- Update NVRAM layout and provide image translation for PST and data collection | Kostadinov, Vladimir | Resolved
26713 | Requirement | *FF -- Factory defaults stored in the device | Hu, Helen | Resolved
26855 | Requirement | *FF -- APP -- Control limits shall be wide enough to accommodate PST limits | Hu, Helen | Resolved
26857 | Requirement | *FF -- PST -- Read of data collected for PST must be available before PST completes | Kostadinov, Vladimir | Resolved
26858 | BugReport | *FF -- FFP PST -- Interface to command 190.22 is broken | Kostadinov, Vladimir | Resolved
26918 | BugReport | FF DLL network parameters: DEV_MRD_MIN=5 shaky, =4 doesn't work | Hu, Helen | Resolved
26919 | BugReport | *FF -- FFP -- Inconsistent state of device - assertion failed | Kostadinov, Vladimir | Resolved
26927 | BugReport | *FF -- Remove/disable IPC profiling when finished with development | Kostadinov, Vladimir | Activated
26933 | Requirement | *FF FFP -- There should be a way to reinitialize FFP NVMEM by a user action | Kostadinov, Vladimir | Resolved
26934 | BugReport | *FFP -- Reinit of NVMEM causes CPU trap 3 | Kostadinov, Vladimir | Resolved
26945 | BugReport | *FF Need to improve robustness of HART master, e.g. MAX_HART_TELEGRAMM_LEN vs. RSP_MAX_PAYLOAD | Kostadinov, Vladimir | Resolved
27023 | Requirement | *FFP -- Need a method to evaluate free CPU time, time of NVMEM test roundtrip, time of flash test roundtrip | Kostadinov, Vladimir | Resolved
27024 | BugReport | *FF - AO FB - Unexpected LO mode | Hu, Helen | Resolved
27046 | BugReport | *FFP -- NVMEM thrashing | Hu, Helen | Resolved
27101 | Requirement | *FF -- Enable physical analog input as a parameter in TB and as an input channel for AI FB | Hu, Helen | Resolved
27242 | BugReport | *FF -- selftest -- flash selftest structure not correctly initialized | Hu, Helen | Resolved
27245 | BugReport | *FF FFP -- NVMEM -- Items subject to NV layout translation must be stored in normal NVRAM, not in log files | Kostadinov, Vladimir | Resolved
27254 | BugReport | *FF -- FFP -- Deferred write of a log file may abort a file read operation | Kostadinov, Vladimir | Resolved
27255 | Requirement | *FF -- FFP -- Provide a means to reset/clear the log file system | Kostadinov, Vladimir | Resolved
27304 | BugReport | *FF -- Travel calibration -- writing stops doesn't clear FAULT_FIND_STOPS_FAILED | Hu, Helen | Resolved
27306 | BugReport | *FF -- Local UI configuration -- UI password is visible in plain text in TB parameter UI_ACCESS_CONTROL | Kostadinov, Vladimir | In Review
27309 | BugReport | *FF -- Factory defaults --Incorrect handling of valve position configuration | Hu, Helen | Resolved
27310 | Requirement | *FF -- Factory defaults interfaces | Hu, Helen | Resolved
27319 | Task | *FF FFP -- NVMEM management -- Finalize layout 0 of FFP NVMEM | Khasin, Ark | Finished
27333 | Requirement | *FF -- Interoperability -- Need to map TB alarms to RB::FD_SIMULATE.DIAGNOSTIC_VALUE | Hu, Helen | Resolved
27334 | Requirement | *FF -- Build -- Provide automation for sharing alarm definitions with RB DD, C and GW | Kostadinov, Vladimir | Resolved
27382 | BugReport | *FF -- "Factory defaults" and "Advanced" -- Incorrect fix-up of enabled alerts | Hu, Helen | Resolved
27383 | BugReport | *FF -- Old-style Record definition in GW should be replaced with new style (sensible names) | Kostadinov, Vladimir | Resolved
27384 | BugReport | *FF -- Incorrect representation of FF Boolean variables | Kostadinov, Vladimir | Resolved
27389 | BugReport | *FF -- Alerts -- Alerts that can't be disabled don't make it to alerts log | Kostadinov, Vladimir | Resolved
27390 | BugReport | *FF -- Units handling -- Change of pressure units is accompanied by one-shot recalculation | Kostadinov, Vladimir | Resolved
27391 | BugReport | *FF -- DO FB -- Output channel FAULT is not wired to anything | Hu, Helen | Resolved
27409 | BugReport | *FF -- TB parameters owned by APP may be used without refresh | Kostadinov, Vladimir | Resolved
27456 | BugReport | *FF -- FFP -- Writing to alert or history alert may increment ST_REV | Hu, Helen | Resolved
27457 | BugReport | *FF -- FFP -- User writes to extremes are stored in NVMEM | Hu, Helen | Resolved
27526 | BugReport | *FF -- FIrmware download crashes FFP | Hu, Helen | Resolved
27535 | BugReport | * FF FP -- Comm -- Wrong response possible | Khasin, Ark | Resolved
27536 | BugReport | *FF FP -- MN_ASSERT is the wrong way to verify input parameters | Kostadinov, Vladimir | Resolved
27537 | BugReport | *FF FP -- Incorrect mn_GetBit | Kostadinov, Vladimir | Resolved
27538 | BugReport | *FF AP -- Quality -- View of raw position value on LCD should not be conditional | Kostadinov, Vladimir | Resolved
27539 | BugReport | *FF FP -- Advanced parameter - Write | Kostadinov, Vladimir | Resolved
27540 | BugReport | FF FP -- Alerts -- Duplicate buggy code in deadband synchronization | Hu, Helen | Resolved
27547 | BugReport | Release folder for device version 3 is missing | Kostadinov, Vladimir | Resolved
27553 | BugReport | Starting code of Data Collection is changed | Kostadinov, Vladimir | Activated
27787 | BugReport | *FFAP -- Mode transition from LO to MAN doesn't fix the setpoint in effect. | Kostadinov, Vladimir | Resolved
27796 | BugReport | *FF -- DO FB -- With Output channel=CH_DO_FAULT, failed state request may become stale | Hu, Helen | Resolved
27808 | BugReport | *FFP -- "Advanced" read filter is catastrophically wrong | Kostadinov, Vladimir | Resolved
27869 | BugReport | *FF -- fstate -- FAULT channel of DO FB latches fstate.Active state | Hu, Helen | Resolved
27928 | Requirement | *FF -- APP -- Disable power switching of Digital Input | Hu, Helen | Resolved
28055 | BugReport | *FF -- FFP -- OFFICIAL build may produce unusable result | Hu, Helen | Resolved
28159 | Requirement | *FF -- Provide "Advanced" key generator software | Hu, Helen | Resolved
28185 | Requirement | *FF -- APP -- Local UI -- The English text of failed UI shall be "TUNE ERR" | Hu, Helen | Resolved
28298 | BugReport | *FF -- APP -- Address multiple problems with autotune | Hu, Helen | Resolved
28676 | Requirement | APP and FFP should use the same i2c and fram drivers | Kostadinov, Vladimir | Resolved
28677 | Task | Clean up the FFP build system w.r.t. folders tree and APP dependencies | Khasin, Ark | Finished
28772 | BugReport | *FFP -- If XD_FSTATE is configured to fail closed (open), ATC valve fails open (resp., closed) instead | Hu, Helen | Resolved
28820 | BugReport | *FFP -- Setpoint work incorrectly due to XD_FSTATE configuration in MAN mode | Hu, Helen | In Review
28831 | Requirement | *FFP -- Enhance TB XD_FSTATE functionality | Hu, Helen | Resolved
28833 | Requirement | *FFP -- Provide a means of adding a block parameter without re-initializing FFP NVMEM | Kostadinov, Vladimir | Resolved
28913 | Requirement | *FF -- Document parameters new to R3 or changed | Kostadinov, Vladimir | Resolved
28932 | Requirement | *FF -- Remove host-based NVMEM translation as under-implemented | Kostadinov, Vladimir | Resolved
28941 | BugReport | *FF -- APP -- Autotune results are not repeatable | Kostadinov, Vladimir | Deferred
28965 | BugReport | *FFP -- NVMEM table for vertran is obsolete and the generator got broken | Kostadinov, Vladimir | Resolved
28969 | Requirement | *FFP -- Create and roll back NVMEM layout increment to test NVMEM translation in FFP | Kostadinov, Vladimir | Resolved
28989 | BugReport | Calculate the Key for Standard and advanced from Visual Studio project | Kostadinov, Vladimir | Activated
29003 | BugReport | *FFP -- When creating a translated image, other writes to NVMEM are possible | Kostadinov, Vladimir | Resolved
29021 | BugReport | *FFP -- never ending refresh state in FF side | Hu, Helen | Resolved
29077 | BugReport | FFP may fail depending on the order of linking | Khasin, Ark | Resolved
29102 | BugReport | *FF -- FFP -- Watchdog tickling from Softing library remains active | Hu, Helen | In Review
29165 | BugReport | *FF FP -- Flash test failure is not sufficiently guarded | Hu, Helen | Resolved
29243 | BugReport | *FFP -- unexpected fault “new diagnostic signature” | Hu, Helen | Resolved
29246 | BugReport | *FFP -- buffer size check breaks IDE code browser | Kostadinov, Vladimir | Resolved
29247 | BugReport | *FFP -- IPC HART -- Need instrumentation for command 177 "Dynamic data exchange" | Hu, Helen | Resolved
29250 | BugReport | Report of the Fault state in AP | Kostadinov, Vladimir | Resolved
29365 | BugReport | *FF APP -- Start data collection with presampling delays timer ticks | Hu, Helen | Resolved
29411 | BugReport | *FFP -- IPC HART -- Problems with error recovery | Hu, Helen | Resolved
29544 | Requirement | *FFP -- IPC HART -- Error recovery | Hu, Helen | Resolved
29609 | Requirement | *FF -- Firmware Download -- should be optimized for balance | Hu, Helen | Resolved
29610 | Requirement | *FF -- IPC "HART Master" -- Must be able to send Async commands from different contexts | Kostadinov, Vladimir | Resolved
31189 | BugReport | RAM allocated to visible source and Softing libraries should be range-separated | Khasin, Ark | Resolved
31252 | BugReport | *FF -- IPC "HART Master" -- Intermittent failure to init default tags on activation | Hu, Helen | Resolved
38768 | BugReport | Stale codebase needs update for compiler, lint, DD environment etc. | Kostadinov, Vladimir | Resolved
38819 | BugReport | Endless looping of REQIMPORT target in FFP | Kostadinov, Vladimir | Resolved
40239 | BugReport | Activation of R3 doesn't enter "download not ready" state | Kostadinov, Vladimir | Deferred
40292 | BugReport | HART task may be used before it is initialized | Hu, Helen | Resolved
40301 | Requirement | *FFP HART - Add number of re-initializations to IPC statistics | Hu, Helen | Resolved
40309 | BugReport | IPC error handling needs improvements | Hu, Helen | Resolved
41787 | BugReport | Loss of IPC communications is not reported in alarms (or elsewhere) | Hu, Helen | In Review
41808 | BugReport | Code automatically modifies target mode | Hu, Helen | Resolved
41836 | BugReport | Device Rev presented incorrectly in FW download dialog box | Hu, Helen | Resolved
41894 | BugReport | APP faults mapping to FF block_err, xd_err_*, FD alerts must be automated | Kostadinov, Vladimir | Resolved
41896 | BugReport | Field Diagnostics recommended action may be set without FD alert and mismatched against xd_error | Khasin, Ark | Resolved
41910 | BugReport | In DO FB, BLK_ERR_READBACK_CHECK_FAILED may be overwritten | Hu, Helen | Resolved
41983 | BugReport | TB: xd_error_pressure and xd_error_temperature have base type u16; must be u8 per FF-902 | Hu, Helen | Resolved
41985 | BugReport | block mode defintions for RB and TB are redefined from standard | Hu, Helen | Resolved
42031 | BugReport | Low pressure is not detected in position cutoff | Hu, Helen | Resolved
42244 | Task | Evaluate and clone applicable work items for SVI II AP discovered in Beaumont case investigation | Zhou, David | Finished
42245 | Requirement | *ALL positioners -- A positioner shall gracefully handle multiple random resets/power cycles | Kostadinov, Vladimir | Resolved
42246 | BugReport | *ALL Positioners -- bugs in control parameters setting | Hu, Helen | Resolved
42247 | BugReport | *ALL Positioners -- control -- Asymmetric bias normalization on save and read | Kostadinov, Vladimir | Resolved
42248 | BugReport | *ALL Positioners -- control -- Bias correction on start-up is contrary to the stated purpose for ATC | Kostadinov, Vladimir | Resolved
42249 | BugReport | *SVI2AP/SVI1K -- control -- Bias correction for temperature on power-up is wrong | Kostadinov, Vladimir | Resolved
42250 | BugReport | *FFAP -- control -- Wrong bias may be saved | Kostadinov, Vladimir | Resolved
42251 | Requirement | *ALL positioners -- A positioner shall gracefully handle change in operating conditions [1] | Kostadinov, Vladimir | Resolved
42252 | BugReport | *Positioners - All - Unmanaged filter for D term | Kostadinov, Vladimir | Resolved
42253 | BugReport | *ALL Positioners -- anti-windup on low pilot pressure doesn't work | Kostadinov, Vladimir | Deferred
42259 | Task | Remove static duration variables in control.c which can be make automatic | Kostadinov, Vladimir | Finished
42260 | Task | Evaluate and select USE_... conditionals in control.c | Kostadinov, Vladimir | Finished
42261 | BugReport | Minimize the possibility of saving wrong bias | Kostadinov, Vladimir | Resolved
42262 | BugReport | Incorrect setting of BIAS_OUT_OF_RANGE fault | Kostadinov, Vladimir | Resolved
42263 | BugReport | Non-atomic access in continuous diagnostics | Kostadinov, Vladimir | Resolved
42282 | BugReport | IPC Setpoint transfer is ignored in APP | Kostadinov, Vladimir | Resolved
42284 | BugReport | TB.ACTIVATE_CONTROL_SET=10 (Restore backup control set) doesn't work | Hu, Helen | Resolved
42285 | BugReport | TB block_err "Power Up" is not cleared when faults are cleared | Hu, Helen | Resolved
42287 | Task | Calibration of APP in-place reset | Hu, Helen | Activated
42529 | BugReport | HART pass-through buffers should be increased to allow all HART commands | Hu, Helen | Resolved
42530 | Requirement | COMPATIBILITY_REV must be 3 | Hu, Helen | Resolved
42550 | BugReport | Incorrect "setpoint timeout" fault | Kostadinov, Vladimir | Resolved
42604 | Requirement | SVI FF abnormal conditions reporting shall be conforming to FF specification | Kostadinov, Vladimir | Resolved
42703 | Requirement | Provide HART command 0 intercept in FFP | Hu, Helen | Resolved
43408 | BugReport | RB Write lock errors - part 2 | Hu, Helen | Resolved
43410 | BugReport | HART over FF commands error | Hu, Helen | Resolved
43474 | Requirement | Provide test infrastructure for SVI FF allowing SA to connect to FFP HART even if APP is not communicating | Hu, Helen | Resolved
43496 | Requirement | Integrate with the latest HART stack for better configuration features | Kostadinov, Vladimir | Resolved
43526 | BugReport | Component configuration fails to rebuild its output on definition change | Kostadinov, Vladimir | Resolved
43597 | Requirement | FW info in APP should report the changeset instead of build month/day | Hu, Helen | Resolved
43676 | Requirement | Include disclosed type definitions and interfaces | Khasin, Ark | Resolved
43767 | BugReport | Incorrect handling of device reset in firmware download/activation | Hu, Helen | Resolved
43768 | BugReport | After reset, downladed firmware fails to activate, with no indication | Hu, Helen | Resolved
43769 | BugReport | Incorrect handling of "flip partition" option in debug command 255.10 | Hu, Helen | Resolved
43812 | BugReport | NVMEM translation in FFP is wrong | Kostadinov, Vladimir | Resolved
44065 | BugReport | *FFP -- FFP fail to watch dog test | Hu, Helen | Resolved
44099 | BugReport | HART Change Position Limits by Command 171,166 failed | Hu, Helen | In Review
44104 | BugReport | XD_ERROR_PRESSURE doesn't update when device is in failsafe | Hu, Helen | Resolved
44122 | Task | Establish and document IPC performance baseline on APP side | Hu, Helen | Activated
44266 | BugReport | RB Mode can switch to OOS due to commissioning alert when FIND STOP occurs | Hu, Helen | Resolved
44275 | Task | IPC HART - remove dependencies on hartcmd.h | Khasin, Ark | Finished
44276 | Task | Create 2 or more decent builds with different NVMEM layouts to test 43812 (linked) | Khasin, Ark | Finished
44277 | BugReport | In AAP NVMEM, replace unused fault masks with LCD cal table | Hu, Helen | Resolved
44279 | BugReport | *FF -- RB -- RESTART processor didn't recover device from IPC lost at all | Hu, Helen | Resolved
44365 | Requirement | RB.fault_state=FAULT_STATE_ACTIVE causes OOS in RB only if propagated from TB | Hu, Helen | Resolved
44369 | Task | TestCase1forBug 44281 | Hu, Helen | Activated
45379 | Requirement | power up shall not be reported in block_err | Hu, Helen | Resolved
50522 | Task | Create macros for DD Record-type parameters automation | Khasin, Ark | Finished
50531 | BugReport | Firmware activation fails if an APP process is (re)triggered | Hu, Helen | Resolved
50600 | BugReport | APP RAM read/write commands don't cover the addressable range | Hu, Helen | Resolved
50601 | BugReport | HART over FF connection shows different revision than HART over ISP | Kostadinov, Vladimir | Resolved
50612 | Requirement | A process leaving data in a diagnostic buffer should not auto-terminate | Kostadinov, Vladimir | Resolved
50671 | Requirement | Data collection trigger conditions should be expanded | Kostadinov, Vladimir | Resolved
51652 | BugReport | NVMEM translation in APP may fail depending on content | Hu, Helen | Resolved
51666 | BugReport | If FFP panics repeatedly, APP goes failsafe | Hu, Helen | Resolved
51667 | Requirement | Expand functionality of FW download manipulation | Hu, Helen | Resolved
51775 | Task | Pass-through HART commands definitions need corrections for Smarts Assistant functionality | Khasin, Ark | Finished
51776 | Requirement | Develop capability of per-component configuration to make compile-time feature selection manageable | Kostadinov, Vladimir | Resolved
51831 | Requirement | Need a countermeasure for failed NVMEM translation in APP in firmware activation | Hu, Helen | Resolved
51987 | Requirement | Use standardized TB parameters as reasonably possible | Kostadinov, Vladimir | Reviewing
52129 | Task | Enhance automation of parameter definitions | Khasin, Ark | Finished
52363 | BugReport | Incorrect help generation | Kostadinov, Vladimir | Resolved
52364 | Requirement | FF build - provide automation for TB alerts definitions | Kostadinov, Vladimir | Resolved
52485 | Requirement | Add lifetime max/min temperatures to TB parameters | Kostadinov, Vladimir | Resolved
52797 | BugReport | Incorrect handling of RB.RESTART | Kostadinov, Vladimir | Resolved
52856 | Requirement | Normal and default TB mode shall be AUTO | Kostadinov, Vladimir | Resolved
52857 | Requirement | Provide supporting interfaces for "jumpers" | Kostadinov, Vladimir | Resolved
53054 | Requirement | NV objects with no user interface to set shall not be "restored to firmware defaults" | Kostadinov, Vladimir | Resolved
53057 | Requirement | There shall be RB.RESTART "Quick Start" option to replace firmware defaults with sensible "quasi-default" values | Kostadinov, Vladimir | Resolved
53062 | BugReport | Incorrect TB.FINAL_POSITION_VALUE_x | Kostadinov, Vladimir | Resolved
53063 | Requirement | *FF FF -- RB Parameters -- NV_CYCLE_T should be more than 0 | Kostadinov, Vladimir | Resolved
53074 | BugReport | Missing special repairs of stateful implementation of alerts | Kostadinov, Vladimir | Resolved
53197 | BugReport | Bugs in TB trends implementation | Kostadinov, Vladimir | Resolved
53206 | Requirement | TB trends specification | Khasin, Ark | Resolved
53247 | BugReport | Travel accumulation trend misses increments <1%/s | Kostadinov, Vladimir | Resolved
53590 | BugReport | TB Pressure extremes parameter doesn't update | Kostadinov, Vladimir | Resolved
53594 | Requirement | Provide an option to add back current and history members to TB.*ALERT | Kostadinov, Vladimir | Resolved
53608 | BugReport | Bugs in R2-style handling of alert/historic_alert in Alert definitions | Kostadinov, Vladimir | Resolved
53610 | BugReport | Time difference calculations may overflow and undeservedly clear alerts and fstate | Kostadinov, Vladimir | Resolved
53611 | BugReport | Ranges of pressure parameters don't change when pressure units change | Kostadinov, Vladimir | Resolved
53638 | BugReport | FD-SW build fails | Kostadinov, Vladimir | Resolved
53769 | BugReport | Local UI SIMULATN menu on entry doesn't show the actual "jumper" state | Kostadinov, Vladimir | Resolved
53772 | BugReport | Position error histogram calculations may overflow | Kostadinov, Vladimir | Resolved
53774 | Requirement | CUTOFF effect on alerts and histograms | Kostadinov, Vladimir | Reviewing